MINIMUM PROJECT PLAN

Coffee Export Value Chain Management System (CEVCMS)

Internal project-team planning document — Appendix 2 format

| Field | Value |
| --- | --- |
| Document Reference | ECTA-CEVCMS-PP-V1.0 |
| Document Type | Minimum Project Plan (Practical Course, Appendix 2) |
| Related Documents | Assignment Description ECTA-CEVCMS-AD-V1.0; SRS ECTA-CEVCMS-SRS-V2.1 |
| Version | 1.0.0 |
| Status | Final — internal project-group document (not sent to client) |
| Date | August 8, 2026 |
| Project Duration | One month (four weeks), per the practical-course workload norm |
| Client (context) | Ethiopian Coffee and Tea Authority (ECTA), Addis Ababa, Ethiopia |

Project Group Members

| Name | Student ID | Phone | E-mail |
| --- | --- | --- | --- |
| Kaleab Bantayehu | ATE/0365/15 | 0988472302 | kaleabbantayehu@gmail.com |
| Yedenekachew Fantahun | ATE/6032/15 | 0926390396 | ydanimations@gmail.com |
| Fistum Adisu | ATE/6077/16 | 0929662092 | fitsumleo05@gmail.com |
| Biniyam Abel | ATE/8191/15 | 0966809349 | biniyamabel54@gmail.com |
| Abel Debalke | ATE/0668/15 | 0900008254 | [insert e-mail] |
| Ephratha Samuel | ATE/2652/15 | 0961145028 | sephratha@gmail.com |
| Kidus Ergetachew | ATE/3349/15 | 0935021105 | kidus.ergetachew21@gmail.com |

# 0. Revision History

| Version | Date | Author(s) | Description of Changes |
| --- | --- | --- | --- |
| 0.1 | Early Week 1 | Project Group | Initial draft, developed in parallel with the first draft of the Assignment Description. |
| 0.2 | Mid Week 1 | Project Group | Revised using the SRS module directory and clarifications from the client interview. |
| 1.0 | End of Week 1 | Project Group | Final version, consistent with the finalized Assignment Description (ECTA-CEVCMS-AD-V1.0) and SRS (ECTA-CEVCMS-SRS-V2.1). |

# 1. Introduction

This Minimum Project Plan is the internal planning document for the Coffee Export Value Chain Management System (CEVCMS) practical-course project. It follows the structure required by Appendix 2 ("The Project Plan") and is written in direct relation to the Assignment Description (ECTA-CEVCMS-AD-V1.0) and the Software Requirements Specification (SRS, ECTA-CEVCMS-SRS-V2.1). Unlike the Assignment Description, this is an internal working document for the project group and supervisors; it is not signed by the client, and it is expected to change as the project proceeds.

The plan converts the objectives and scope already agreed with the client into a concrete, one-month execution plan: a work breakdown structure, a four-week schedule, task ownership, dependencies, resources, risks, and a quality and testing approach. Where the Assignment Description defines what is to be delivered and why, this Project Plan defines how, by whom, and when.

Consistent with Appendix 2, this plan is expected to be revised during the project as realized progress deviates from the original schedule. Such deviations do not require a new Assignment Description; they are handled through the progress-control mechanism described in Section 4.4.

# 2. Basic Assumptions

## 2.1 Problem Definition and Objectives

The problem definition and the project objectives are defined in full in the Assignment Description (Sections 4 and 5) and are not repeated here; this Project Plan refers to them directly. In summary:

- Core objectives (O1, O2) — replacing paper waybills, grading certificates, and export permits with digitally verifiable records, and providing farm-to-lot origin traceability — are delivered through the core-scope modules in Section 7 of this plan.

- Stretch objectives (O3, O4) — automated export/forex cross-validation and reduced clearance lead time — are attempted only after the core scope is implemented and tested, as agreed in Assignment Description Section 5.

- Objective O5 (farmer price and receipt visibility) is delivered to the extent supported by the Authentication and Farmer & Polygon Registry modules; live SMS/USSD delivery is out of scope (Assignment Description Section 8.2) and is represented in the working increment as an in-app/simulated notification.

## 2.2 Deliverables

The following products will be delivered over the course of the project. This list is consistent with Assignment Description Section 7.1.

| Deliverable | Description |
| --- | --- |
| Assignment Description | Already finalized (ECTA-CEVCMS-AD-V1.0); defines problem, objectives, and scope. |
| Project Plan | This document; internal execution plan for the project group. |
| Design Document | Data model (ERD), architecture diagram, and module interaction diagrams for the selected SRS modules, completed by Milestone M3. |
| Working Software Increment | Implemented and tested subset of CEVCMS functionality, scoped to the modules in Section 7 of this plan, delivered by Milestone M4. |
| Test Report | Evidence of unit, integration, and functional/system testing of the delivered increment (Section 6.4). |
| Progress Reports | Biweekly reports to the supervisor, per Appendix 3. |
| Final Presentation and Demonstration | Presentation to the client and steering committee at project closure (M6), demonstrating the delivered increment against Assignment Description Section 5. |

## 2.3 References

- Assignment Description for the Coffee Export Value Chain Management System, ECTA-CEVCMS-AD-V1.0.

- Software Requirements Specification (SRS) for CEVCMS, ECTA-CEVCMS-SRS-V2.1.

- University Practical Course, Appendix 1 — Assignment Description.

- University Practical Course, Appendix 2 — Minimum Project Plan.

- University Practical Course, Appendix 3 — Minimum Progress Report.

# 3. Project Organization

## 3.1 Tasks, Powers, and Responsibilities

Each project member owns one core deliverable area while sharing integration, testing, documentation, and presentation duties, so that no single member carries the full workload for any of those cross-cutting activities. Names below follow the roster supplied by the project group; replace the one missing e-mail address before submission.

| Member | Primary Role | Primary Module / Area (SRS reference) | Shared Responsibilities |
| --- | --- | --- | --- |
| Kaleab Bantayehu | Project Manager & Backend Lead | Authentication & Role-Based Access (FR-AUTH; MOD-01/MOD-02) | Progress control, client/supervisor liaison, integration |
| Yedenekachew Fantahun | Database Lead & Backend Developer | Farmer & Polygon Registry (FR-FARM; MOD-03) — schema and API | Database schema ownership, integration, testing |
| Fistum Adisu | Backend Developer | Traceability & Dynamic QR Engine (FR-TRACE; MOD-06/07) | Integration, testing, technical documentation |
| Biniyam Abel | Frontend Lead | Web portal UI for all in-scope modules (Angular/React per Section 5.1) | UI/UX consistency, wireframes, demo staging |
| Abel Debalke | Backend Developer | Stretch: Quality Grading & Waybill Issuance (FR-QUAL, FR-LOG) | Integration, testing, documentation |
| Ephratha Samuel | Backend Developer & QA Lead | Stretch: Export Licensing & Forex Cross-Validation (FR-EXP) | Test planning and execution, defect tracking |
| Kidus Ergetachew | QA & Documentation Lead | Test Report, user manual, final report compilation | Presentation preparation, biweekly progress reports |

Quality control is the joint responsibility of Kidus Ergetachew (QA & Documentation Lead) and Ephratha Samuel (QA Lead), who review test coverage and defect status ahead of each milestone. Kaleab Bantayehu, as Project Manager, is responsible for schedule tracking, escalation of blockers to the supervisor, and sign-off that a milestone's deliverables are complete before it is reported as achieved.

## 3.2 Project Environment

The direct stakeholders of the project group are:

- The client, ECTA, represented by a designated client contact (to be confirmed per Assignment Description Section 13); the project group expects timely answers to scoping questions and written feedback at each milestone.

- The steering committee, which reviews and signs off deliverables sent to the client, per Assignment Description Section 1.

- The practical-course supervisor(s), who receive the biweekly progress report and review internal deliverables (this Project Plan, the Design Document, the Test Report) before they are finalized.

- The project group itself, whose internal task allocation is defined in Section 3.1.

The project group expects the client and supervisors to provide scoping decisions at Milestone M3 (see Section 7.2) and written review comments within the timeframes agreed in Assignment Description Section 13; delays beyond those timeframes are treated as a risk (Section 4.3, RSK-05).

# 4. Project Management

## 4.1 Management Targets

The project group's management targets for the one-month practical course are:

- Deliver the three core-scope modules (Authentication & RBAC, Farmer & Polygon Registry, Traceability & QR Engine) fully functional and tested by Milestone M4 (end of Week 3).

- Attempt the two stretch-scope modules (Quality Grading & Waybill Issuance, Export–Forex Cross-Validation) only after the core scope is complete, and report honestly at M4/M5 which stretch items were reached.

- Keep the schedule realistic for a one-month, part-time student project: no task is scheduled assuming more than the group's available person-hours per week (Section 7.4).

- Maintain a working, demonstrable increment at all times after Week 2, rather than a single large integration attempt in Week 4.

## 4.2 Assumptions and Dependencies

These carry forward directly from Assignment Description Section 14 and apply to the plan below:

- The delivered increment is a demonstration-scale prototype, not a national production system; performance and infrastructure targets in SRS Section 5 and Section 14 (e.g., 5,000 TPS peak throughput, multi-region Kubernetes deployment) are enterprise-programme targets and are not pursued in Version 1.0.

- External integrations (NBE, ECC, commercial banks, telecom USSD/SMS gateways, GPS/IoT providers) are represented as simulated or stubbed interfaces, consistent with Assignment Description Section 8.1; no production credentials or live gateways are required.

- No real farmer, financial, or trade data will be used; all pilot data is synthetic or anonymized, consistent with Assignment Description Section 14.

- The offline-first Android application and the Offline Synchronization Engine (SRS MOD-11 / FR-SYNC) are not part of the one-month implementation scope; the working increment is delivered as a web application, and offline behavior is discussed only as a design consideration in the Design Document.

- The project group depends on timely scope confirmation from the client and supervisors at Milestone M3 (mid Week 2); a delay here directly compresses the implementation weeks (Weeks 2–3).

## 4.3 Risk Control

Risks are project-group-level delivery risks for the one-month timeframe, distinct from the enterprise-scale risk register in SRS Section 12 (which concerns the full national programme and is out of scope here).

| # | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| RSK-01 | One month is not enough time to complete even the core scope. | Medium | High | Core scope limited to 3 modules; stretch scope explicitly deferred first if time runs short (per Assignment Description Section 5). |
| RSK-02 | Scope creep — team adds SRS features beyond the agreed Section 8.1 scope. | Medium | Medium | All tasks in the WBS (Section 7.1) are traced to an in-scope FR ID; the PM rejects untraced tasks at weekly review. |
| RSK-03 | Integration problems when merging Auth, Farmer Registry, and Traceability modules. | Medium | Medium | Shared API contracts and DB schema agreed at design time (M3); integration attempted incrementally from Week 2, not left to Week 4. |
| RSK-04 | Database or backend defects discovered late (e.g., PostGIS polygon logic). | Medium | Medium | Early spike/prototype of the polygon-capture and EUDR-flag logic in Week 1–2; unit tests written alongside the code, not after. |
| RSK-05 | Team coordination issues or uneven workload across 7 members. | Low | Medium | Fixed module ownership (Section 3.1) with shared cross-cutting duties; PM tracks task completion at each weekly meeting (Section 4.4). |
| RSK-06 | Testing delayed to the last days of the project. | Medium | High | Testing is a continuous WBS category (Section 7.1), not a Week-4-only activity; each module is unit-tested as it is completed. |
| RSK-07 | Technical learning curve for GIS/PostGIS (polygon capture, area/EUDR-flag logic) or QR/cryptographic signing. | Medium | Medium | Time-boxed in Week 1 as a design spike; fallback to a simplified area/point-radius EUDR check (per SRS FR-FARM-002) if full polygon topology validation is not feasible in time. |
| RSK-08 | Dependency on client/supervisor scope confirmation at M3. | Low | High | Draft scope decision proposed by the project group ahead of M3 so confirmation, not fresh scoping, is what is required from the client. |

## 4.4 Progress Control

Progress is controlled at three levels:

- Task level: a shared task board (GitHub Projects/Issues) lists every WBS task from Section 7.1 with an owner, status, and target week; the Project Manager reviews it before each weekly meeting.

- Weekly level: a short team meeting (in person or online) reviews tasks completed, tasks at risk, and re-assigns work if a member is behind or ahead; action items are logged in the meeting notes.

- Milestone level: at each milestone in Section 7.2 (M3–M6), the Project Manager confirms against the WBS and deliverables table (Section 2.2) whether the milestone's associated deliverable is actually complete before it is reported as achieved.

If a task cannot be completed as scheduled, the group first checks whether it can be re-sequenced within the remaining weeks without displacing core-scope work; if not, stretch-scope tasks (Section 7.1, WBS items marked "Stretch") are the first to be dropped, consistent with the priority already agreed in Assignment Description Section 5.

# 5. Technical Procedure

## 5.1 Methods, Techniques, and Tools

The project group follows the incremental, requirements-driven approach already committed to in Assignment Description Section 6: modules are implemented in SRS priority order, core scope first, so that the highest-priority regulatory and traceability functions are working before any stretch-scope work begins.

| Layer | Technology (Version 1.0, demonstration scale) | Notes |
| --- | --- | --- |
| Frontend (web) | Angular or React with a component library; Leaflet/Mapbox GL for polygon drawing | Consistent with SRS Section 4.1 web-stack direction; no native Android build in Version 1.0. |
| Backend API | REST API (e.g., Node.js/Express or Python FastAPI — team's choice, confirmed at design time) | One consistent framework across all modules to simplify integration. |
| Database | PostgreSQL with the PostGIS extension | PostGIS is required for storing and validating farm polygons (FR-FARM-002); a local/managed instance, not the multi-region cluster in SRS Section 14. |
| Authentication | JWT-based session tokens; password hashing (bcrypt/argon2) | Scaled-down version of SRS FR-AUTH-001; OTP/MFA and HSM-backed signing are out of scope for Version 1.0. |
| QR / traceability | Server-generated QR codes (e.g., a QR-code library) encoding a verification URL and lot ID; HMAC signature over the payload | Demonstrates SRS FR-TRACE-002 principle at prototype scale, without a hardware security module. |
| Version control | Git, hosted on GitHub (private repository) | Feature-branch workflow; pull requests reviewed by at least one other member before merge. |
| Project tracking | GitHub Projects / Issues (task board) | Referenced in Section 4.4. |
| API testing | Postman or equivalent | Used for manual and scripted integration tests (Section 6.4). |

Technologies not listed above — AI/ML components, blockchain, IoT sensor integration, live SMS/USSD gateways, bank/customs APIs, and multi-region Kubernetes deployment — are part of the SRS enterprise vision (SRS Section 15, "Future Enhancements & EUDR Roadmap") and are explicitly not implemented in this one-month project, consistent with Assignment Description Section 8.2.

## 5.2 Support and Configuration Management

- Source control: a single shared GitHub repository with a main branch protected from direct pushes; all work merged via reviewed pull requests.

- Environment: each member develops locally (Section 7.4, Resources); a shared cloud database instance (e.g., a free-tier managed PostgreSQL/PostGIS service) is used from Week 2 onward so members work against the same schema and seed data.

- Configuration: environment variables (DB credentials, JWT secret, QR signing key) kept out of source control via a template `.env.example` file; no production secrets are used since no live external systems are integrated.

- Backups: the shared database is exported (pg_dump) before major schema changes so integration mistakes can be rolled back without losing seeded demo data.

# 6. Quality Plan

## 6.1 Documentation Plan

Every project document (Assignment Description, this Project Plan, Design Document, Test Report, Progress Reports, Final Report) is written in a single shared style and must state: author(s), reviewer(s), a revision history table, a version number, and a status indication (Draft / Under Review / Final). Documents are stored in a shared project drive/repository folder organized by document type, so the current version is always unambiguous.

## 6.2 Review Plan

Any document intended for the client (the Assignment Description and the Final Presentation materials) is reviewed by the full project group and by the supervisor before being sent, consistent with Appendix 1. Internal documents (this Project Plan, the Design Document, the Test Report) are reviewed by at least one member other than the author before being marked "Final". Code changes are reviewed via pull request by at least one other project member before merging to the main branch.

## 6.3 Internal Communication Plan

- Weekly team meeting (Section 4.4) for task review and re-planning.

- A shared chat channel (e.g., Telegram/WhatsApp group already used by the team) for day-to-day coordination and quick blockers.

- The GitHub task board as the single source of truth for "what is done, what is in progress, what is blocked", so status is visible between meetings.

## 6.4 Quality Assurance and Testing Plan

Testing is scaled to what is realistically achievable by a 7-person student team in one month; it targets confidence in the delivered increment's functional correctness, not the enterprise-scale test matrix in SRS Section 13 (e.g., peak-load performance testing and full OWASP penetration testing are out of scope).

| Test Level | Target Scope (Version 1.0) | Approach |
| --- | --- | --- |
| Unit testing | Business-logic functions: net-weight calculation, EUDR area/overlap flagging, minimum-price check, QR payload signing | Automated unit tests (e.g., Jest/PyTest, matching the chosen backend framework), written by the module owner alongside the code. |
| Integration testing | REST API endpoints and database interactions for each in-scope module | Postman collections run manually and, where time allows, via a simple CI script. |
| Functional / system testing | End-to-end use cases: farmer + polygon registration → EUDR flag → traceable lot → QR generation → (stretch) grading/waybill/export checks | Manual walkthroughs against the acceptance criteria in Assignment Description Section 12, using seeded demonstration data. |
| Role-permission validation | RBAC rules for each in-scope user role (Farmer-facing staff, Coop/Field roles, ECTA officer, Exporter, Admin) | Manual test matrix: each role attempts an allowed and a disallowed action; unauthorized actions must be rejected. |
| Input validation & error handling | Form and API input validation (required fields, weight/moisture ranges, polygon vertex counts) | Boundary-value and invalid-input test cases per module. |
| Basic security checks | Password hashing, JWT validation/expiry, parameterized queries (SQL-injection prevention via ORM) | Manual verification checklist; no formal penetration test. |
| User acceptance / demo testing | Full increment against Assignment Description Section 5 objectives | Rehearsed internal demo before Milestone M5, using the same script planned for the client demonstration. |

Results are compiled into the Test Report deliverable (Section 2.2), which records, for each tested requirement, the test performed, the outcome, and any open defects, consistent with Assignment Description Section 12 ("Test Report Review").

# 7. Planning

This section integrates the deliverables, activities, and milestones already agreed in the Assignment Description into a single, detailed execution plan for the project group, as required by Appendix 2.

## 7.1 Work Breakdown Structure

Tasks are grouped into ten categories. Every implementation task is traced to a specific SRS functional requirement (FR ID) so that no task is scheduled outside the agreed scope (Assignment Description Section 8.1). Tasks marked "Stretch" belong to Objectives O3/O4 and are only started once the corresponding core-scope row is complete.

### 1. Project Initiation & Planning

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Confirm module/use-case scope with client and supervisors | AD Sec. 8 | Kaleab Bantayehu (PM) | Confirmed scope note (feeds M3) |
| Set up GitHub repository, branching model, and task board | PP Sec. 5.2 | Kaleab Bantayehu | Repository + task board |
| Set up shared development/database environment | PP Sec. 5.1 | Yedenekachew Fantahun | Shared PostgreSQL/PostGIS instance |

### 2. Requirements & Analysis

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Review SRS module directory and select pilot use cases per module | AD Sec. 6, Sec. 8.1 | Full team | Use-case list per module |
| Define acceptance criteria per module from SRS FR sections | SRS Sec. 3 | Kidus Ergetachew | Acceptance-criteria checklist |

### 3. System Design

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Design overall web-app architecture (frontend / API / DB) | SRS Sec. 2.1, 4 | Fistum Adisu | Architecture diagram |
| Design database schema: farmers, farms/polygons, users/roles, lots/batches, traceability links, and stretch-scope tables | SRS Sec. 7 | Yedenekachew Fantahun | ER diagram + DDL scripts |
| Design UI wireframes for login, farmer/polygon registration, traceability/QR view, and stretch screens | SRS Sec. 4.1 | Biniyam Abel | Wireframe set |

### 4. Database Development

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Implement tbl_users / roles / permissions schema | FR-AUTH, MOD-02 | Yedenekachew Fantahun | Migrated schema |
| Implement tbl_farmers and tbl_farms (PostGIS) schema | FR-FARM-001/002 | Yedenekachew Fantahun | Migrated schema |
| Implement lot/batch and traceability-link schema | FR-TRACE-001 | Fistum Adisu | Migrated schema |
| (Stretch) Implement quality-certificate and e-waybill schema | FR-QUAL, FR-LOG-001 | Abel Debalke | Migrated schema |
| (Stretch) Implement export-contract schema | FR-EXP-001 | Ephratha Samuel | Migrated schema |

### 5. Backend Development

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Implement login, JWT issuing, and RBAC middleware | FR-AUTH-001 | Kaleab Bantayehu | Auth API |
| Implement role/permission management endpoints | MOD-02 | Kaleab Bantayehu | RBAC API |
| Implement farmer profile CRUD + FIN generation | FR-FARM-001 | Yedenekachew Fantahun | Farmer API |
| Implement polygon capture, area calculation, and EUDR overlap flag | FR-FARM-002 | Yedenekachew Fantahun | Polygon API |
| Implement lot/traceability lineage linking (farmer → farm → lot) | FR-TRACE-001 | Fistum Adisu | Traceability API |
| Implement QR generation + verification endpoint | FR-TRACE-002 | Fistum Adisu | QR generation/verification API |
| (Stretch) Implement Q-Grading entry + certificate issuance | FR-QUAL-001/002 | Abel Debalke | Grading API |
| (Stretch) Implement e-Waybill issuance | FR-LOG-001 | Abel Debalke | Waybill API |
| (Stretch) Implement export-contract registration + minimum-price check | FR-EXP-001 | Ephratha Samuel | Export API |
| (Stretch) Implement simulated forex-verification cross-check | FR-EXP-002 | Ephratha Samuel | Forex-check API (simulated) |

### 6. Frontend Development

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Build login / role-aware navigation shell | FR-AUTH-001 | Biniyam Abel | Auth UI |
| Build farmer registration + interactive polygon-drawing map form | FR-FARM-001/002 | Biniyam Abel | Farmer/polygon UI |
| Build traceability lineage view + QR display/download | FR-TRACE-001/002 | Biniyam Abel | Traceability UI |
| (Stretch) Build grading and waybill entry screens | FR-QUAL, FR-LOG-001 | Biniyam Abel | Grading/waybill UI |
| (Stretch) Build export-contract and forex-check screens | FR-EXP-001/002 | Biniyam Abel | Export UI |

### 7. Integration

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Integrate Auth + RBAC across all module APIs | FR-AUTH-001 | Kaleab Bantayehu | Integrated auth layer |
| Integrate Farmer/Polygon module with Traceability module | FR-FARM, FR-TRACE | Fistum Adisu, Yedenekachew Fantahun | End-to-end farm-to-lot chain |
| Integrate stretch modules with core chain (if reached) | FR-QUAL, FR-LOG, FR-EXP | Abel Debalke, Ephratha Samuel | Extended chain (stretch) |

### 8. Testing

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Unit tests for core business logic (weights, EUDR flag, QR signing) | PP Sec. 6.4 | Module owners | Unit test suite |
| Integration tests for module APIs (Postman) | PP Sec. 6.4 | Ephratha Samuel | Postman collections + results |
| Functional/system walkthrough of full traceability use case | AD Sec. 12 | Kidus Ergetachew | Test Report (draft) |
| Role-permission and input-validation test pass | PP Sec. 6.4 | Ephratha Samuel | Test matrix results |

### 9. Documentation

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Compile Design Document (architecture, ERD, wireframes) | AD Sec. 7.1 | Kidus Ergetachew | Design Document |
| Compile Test Report | AD Sec. 7.1, 12 | Kidus Ergetachew | Test Report (final) |
| Write user manual for the delivered increment | PP Sec. 2.2 | Kidus Ergetachew | User manual |
| Write biweekly progress reports (Appendix 3 format) | AD Sec. 11 | Kidus Ergetachew (with PM sign-off) | Progress reports x2 |

### 10. Final Presentation & Demo Preparation

| Task | Traces to | Owner | Deliverable |
| --- | --- | --- | --- |
| Prepare demonstration script covering AD Section 5 objectives | AD Sec. 12 | Kidus Ergetachew, Kaleab Bantayehu | Demo script |
| Rehearse end-to-end demo with seeded data | AD Sec. 12 | Full team | Rehearsed demo |
| Deliver final presentation and demonstration to client | AD Sec. 9 (M6) | Full team | Final Presentation and Demonstration |

## 7.2 Four-Week Schedule

Calendar dates are fixed once the practical-course schedule is confirmed; the week numbers below are relative to the start of the course and align with the milestones already agreed in Assignment Description Section 9.

| Week | Focus | Key Activities | Milestone |
| --- | --- | --- | --- |
| Week 1 | Initiation, finalization of planning documents, design | Finalize Assignment Description and this Project Plan; confirm draft module scope ahead of the client interview; design system architecture and database schema; produce UI wireframes; set up repository, task board, and shared dev/DB environment. | M1 — Assignment Description Agreed; M2 — Project Plan Approved (both end of Week 1) |
| Week 2 | Design finalization and core module build-out begins | Confirm final pilot scope with client/supervisors; complete Design Document; implement database schema; begin Authentication & RBAC and Farmer & Polygon Registry (backend + frontend), including polygon capture and EUDR flag logic. | M3 — Scope and Design Finalized (mid Week 2) |
| Week 3 | Core module completion and integration; stretch scope begins if ahead of plan | Complete Traceability & QR Engine; integrate Auth, Farmer Registry, and Traceability into one working chain; run unit and integration tests as each piece lands; begin stretch modules (Quality Grading & Waybill Issuance, Export–Forex Cross-Validation) only once the core chain is demonstrable end to end. | M4 — Working Increment Delivered (end of Week 3) |
| Week 4 | System testing, bug fixing, documentation, and demonstration | Functional/system and role-permission testing; fix defects found; finish stretch-scope work if time allows and cleanly stop it (mark as future work) if not; compile Test Report, user manual, and final report; rehearse and deliver the final demonstration. | M5 — Client Acceptance Review (mid Week 4); M6 — Project Closure (end of Week 4) |

## 7.3 Task Dependencies

The core implementation chain has a single critical path; stretch-scope modules branch off it once the core chain is stable, and can be developed in parallel with each other because Quality Grading/Waybill Issuance and Export–Forex Cross-Validation do not depend on one another (only on the traceable lot record produced by the core chain):

- Database schema (users/roles, farmers, farms/polygons, lots, traceability links) — must exist before any API work starts.

- → Authentication & RBAC API — required by every other module, since all endpoints are role-protected.

- → Farmer & Polygon Registry API — produces the farmer/farm/lot records the Traceability module links.

- → Traceability & QR Engine API — depends on Farmer & Polygon Registry data; completes the core-scope chain (Objectives O1/O2).

- → (Stretch, parallel) Quality Grading & Waybill Issuance, and Export–Forex Cross-Validation — both depend on a traceable lot existing, but not on each other.

- → Frontend integration — each screen is wired to its API only after that API is functionally stable, to avoid rework.

- → System testing — functional/system and acceptance-style testing follows integration of each module, not just at the end of Week 4.

Where genuinely independent (e.g., UI wireframing in Week 1 alongside schema design, or the two stretch modules in Week 3–4), tasks are run in parallel across team members rather than sequentially, to fit the one-month timeframe.

## 7.4 Resource Allocation

### Human Resources

Seven project-group members (Section 3.1), each assumed available at the standard practical-course workload norm for a one-month course; no member is scheduled at a load significantly above or below the others across the four weeks.

### Hardware

- Members' own laptops for development; no dedicated project hardware is procured.

- No physical Bluetooth scales, handheld scanners, or industrial devices are required, since the offline/field hardware integrations in SRS Section 4.2 are out of Version 1.0 scope.

### Software / Development Tools

- Git/GitHub (source control, task board), code editor (e.g., VS Code), Postman (API testing).

- PostgreSQL + PostGIS (local or free-tier managed instance), backend framework runtime (Node.js or Python), frontend framework (Angular or React) and a mapping library (Leaflet/Mapbox GL) for polygon capture.

- draw.io/Figma (or equivalent) for the architecture diagram and wireframes in the Design Document.

### Infrastructure

- A single free-tier or low-cost cloud instance (e.g., Render/Railway/similar) hosting the demo build for Week 4 presentations — not the multi-region Kubernetes production infrastructure in SRS Section 14, which is out of scope.

- Shared cloud storage (e.g., Google Drive) for documents.

### Documentation / Reference Resources

- Assignment Description ECTA-CEVCMS-AD-V1.0 and SRS ECTA-CEVCMS-SRS-V2.1 as the authoritative source of requirements (Assignment Description Section 13).

- Appendices 1–3 as the format reference for the Assignment Description, this Project Plan, and the biweekly progress reports.

# 8. Communication and PR

This section plans how the project group promotes and reports the project to the client and supervisor, alongside the internal communication already described in Section 6.3.

- An informal status update is shared with the ECTA client contact at each major milestone (M3–M6), per Assignment Description Section 11.

- A biweekly progress report is sent to the supervisor by e-mail, in the Appendix 3 format (Section 2.2, "Progress Reports").

- The final demonstration (M6) is scheduled and confirmed with the client and steering committee at least a few days in advance, with the demo script (WBS item 10) shared beforehand so reviewers know what will be shown.

- Any deviation from this plan that affects a client-visible milestone (e.g., a stretch-scope module being dropped) is communicated to the client contact proactively, not left for the M5 acceptance review to surface.

End of Minimum Project Plan — ECTA-CEVCMS-PP-V1.0